## WP
WPICMM WORK PLAN (2018-2022)
V1: 5/7 March 2018 // V2: 12/14 Feb 2020
Version 3: 15/17 Feb 2021
| Description | Q1 / 2018 | Q2 / 2018 | Q3 / 2018 | Q4 / 2018 | Q1 / 2019 | Q2 / 2019 | Q3 / 2019 | Q4 / 2019 | Q1 / 2020 | Q2 / 2020 | Q3 / 2020 | Q4 / 2020 | Q1 / 2021 | Q2 / 2021 | Q3 / 2021 | Q4 / 2021 | Q1 / 2022 | Q2 / 2022 | Q3 / 2022 | Q4 / 2022 | Priorities | Responsibility | Objective(s) | OVIs | Notes | Status January 2021 | Status December 2019 | Status 15/12/2018 | Status 06/09/2018
WPICMM Work Plan
1 | Examine all aspects of CPCs technical implementation of CMMs and recommending ways to enhance the level of implementation
1.1 | Produce dashboard of compliance with CMMs for all CPCs and have this online
1.1.1 | Create dashboard showing compliance with CMMs from national reports and put on secured part of the IOTC website so it is visible to all CPCs | [20 empty] | High | Secretariat | Creating the dashboard to have platform to check the performance of CPCs |  |  | [On going] This activity is being implemented under the e-MARIS project. Three IT experts have been recruited by SWIOFISH2. The e-MARIS project is currently in the Phase III Construction, which is expected to produce the following deliverables: • e-Maris Release V1 • online Record of Authorised Vessels | [Pending] To be implemented under e-MARIS Recruitment of 3 IT experts by SWIOFISH/IOC terminated in 2019. Developpement of e-MARIS started as well as online RAV. | [Pending] To be implemented under e-MARIS Recruitment of 2 IT experts by SWIOFISH/IOC ongoing
1.1.2 | CPCs to add information to dashboard by reporting deadlines | [20 empty] | High | CPCs | To have all CPCs reporting the required information on time |  | This should be done after the complliance form is submitted- April | [On going] This activity is being implemented under the e-MARIS project. Three IT experts have been recruited by SWIOFISH2. The e-MARIS project is currently in the Phase III Construction, which is expected to produce the following deliverables: • e-Maris Release V1 • online Record of Authorised Vessels | Same as above | Same as above
1.1.3 | Rank the CMMs/reporting requirements by priority (i.e which are most critical to report upon) | [20 empty] | High | Secretariat / WPICMM | To rank the CMMs in a way you can determine importance of compliance. |  |  | [Implemented] Analyses provided in Consultant’s report, IOTC-2019-WPICMM02-Compliance review. | [Implemented] Analyses providedConsidered inunder cConsultant’s report, IOTC-2019-WPICMM02-Compliance review. | [On going] Considered under consultant report IOTC-2019-WPICMM02-Compliance review.
1.1.4 | Define a weighting scheme to the P/C assessment of the reporting requirements | [20 empty] | High | Secretariat / WPICMM | To define a weighting scheme for P/C |  | Secretariat to produce a weighting scheme for discussion at the WPICMM | [Implemented] Analyses provided in Consultant’s report, IOTC-2019-WPICMM02-Compliance review. | Same as above | Same as above
1.2 | Prioritise CMMs with lowest implementation levels to determine common issues with compliance
1.2.1 | Use CPCs Compliance Assessment results to determine common challenges and difficulties with compliance | [20 empty] | High | Secretariat &CPCs | Identify difficulities of CPCs in complying with the resolutions |  | Send out by Q3 and return before end of Q4 | [Implemented] Considered in document IOTC-2019-WPICMM02-04 and Consultant’s report IOTC-2019-WPICMM02-Compliance review. | [Implemented] Considered under in paper document IOTC-2019-WPICMM02-04 and cConsultant’s report IOTC-2019-WPICMM02-Compliance review. | [On going] Considered under paper IOTC-2019-WPICMM02-04 and consultant report IOTC-2019-WPICMM02-Compliance review. | To produce paper for WPICMM02 for distribution before end of september
1.2.2 | Follow up with interviews with CPCs to gather more detail | [20 empty] | High | Secretariat | Identify difficulities of CPCs in complying with the resolutions |  |  | [Implemented] CPCs provided more details during WPICMM02 | [Implemented] CPCs provided more details during WPICMM02 | [On going] CPCs to provide more details during WPICMM02
1.2.3 | Recommend a plan to improve compliance could include; specific training events, amendments to reporting requirements, data analysis assistance | [20 empty] | High | WPICMM | Solving difficulities of CPCs in complying with the resolutions |  |  | [Pending] WPICMM04 to make recommendations. | [On going] WPICMM03 to make recommendations | [On going] WPICMM02 to make recommendations
2 | Examine Monitoring, Control and Surveillance (MCS) technical matters in order to provide the Compliance Committee with options for strengthening MCS
2.1 | Improve IOTC MCS scheme
2.1.1 | Review CPCs national MCS scheme and current MCS practices | [20 empty] | Medium | Secretariat |  |  |  | [Implemented] Considered in paper IOTC-2019-WPICMM02-05 and consultant report IOTC-2019-WPICMM02-VMS study & IOTC-2019-WPICMM02-MCS study. [Pending] Recruitment of consultant to review CPCs national MCS scheme and current MCS practices. | [Implemented] Considered under paper IOTC-2019-WPICMM02-05 and consultant report IOTC-2019-WPICMM02-VMS study & IOTC-2019-WPICMM02-MCS study. | [On going] Considered under paper IOTC-2019-WPICMM02-05 and consultant report IOTC-2019-WPICMM02-VMS study & IOTC-2019-WPICMM02-MCS study. | To check with MCS consultant
2.1.2 | Review existing IOTC MCS tools | [20 empty] | Medium | Secretariat |  |  |  | [Implemented] Considered under paper IOTC-2019-WPICMM02-05 and consultant report IOTC-2019-WPICMM02-VMS study & IOTC-2019-WPICMM02-MCS study. | [Implemented] Considered under paper IOTC-2019-WPICMM02-05 and consultant report IOTC-2019-WPICMM02-VMS study & IOTC-2019-WPICMM02-MCS study. | [On going] Considered under paper IOTC-2019-WPICMM02-05 and consultant report IOTC-2019-WPICMM02-VMS study & IOTC-2019-WPICMM02-MCS study. | Will be conducted within the MCS study
2.1.3 | Review upcoming MCS reports comprising of reports on VMS and CDS | [20 empty] | Medium | WPICMM |  |  |  | [Implemented] Report presented at WPICMM02 for review | [Implemented] Report presented at WPICMM02 for review | [On going] Report to be presented at WPICMM02 for review
2.1.4 | Recommendation that the VMS and CDS study reports are submitted to the WPICMM | [20 empty] | Medium | WPICMM |  |  | Should be done before May when CC meets | [Implemented] Report presented at WPICMM02 for review | [Implemented] Report presented at WPICMM02 for review | [On going] Report to be presented at WPICMM02 for review
2.1.4 | Make recommendations on these reports for the Compliance Committee | [20 empty] | Medium | WPICMM |  |  | Should be done before May when CC meets | [Implemented] WPICMM02 makes recommendations | [Implemented] WPICMM02 makes recommendations | [On going] WPICMM02 to make recommendations
3 | Review the reporting requirements contained within CMMs in order to harmonize and streamline
3.1 | Review reporting requrements in all CMMs
3.1.1 | Assess and compare reporting requirements for all CMMs in other relevant RFMOs and harmonize | [20 empty] | Medium | Consultant | Simplify reporting requirements |  |  | [Implemented] Considered in paper IOTC-2019-WPICMM02-06 and consultant report IOTC-2019-WPICMM02-Compliance review. | [Implemented] Considered under paper IOTC-2019-WPICMM02-06 and consultant report IOTC-2019-WPICMM02-Compliance review. | [On going] Considered under paper IOTC-2019-WPICMM02-06 and consultant report IOTC-2019-WPICMM02-Compliance review. | Establish ToR by end of september
3.1.2 | Undertake an assessment of existing IOTC reporting requirement in order to streamline the reporting by CPCs | [20 empty] | High | Secretariat | Simplify reporting requirements |  |  | [Implemented] Considered in paper IOTC-2019-WPICMM02-06 and consultant report IOTC-2019-WPICMM02-Compliance review. | [Implemented] Considered under paper IOTC-2019-WPICMM02-06 and consultant report IOTC-2019-WPICMM02-Compliance review. | [On going] Considered under paper IOTC-2019-WPICMM02-06 and consultant report IOTC-2019-WPICMM02-Compliance review. | See above (ToR for the two line)
3.1.3 | Consider the report at WPICMM | [20 empty] | Medium | WPICMM | Simplify reporting requirements |  | Make recommendations to Secretariat to complete 3.1.4 | [Implemented] Consultant report IOTC-2019-WPICMM02-Compliance review to be reviewed by WPICMM02. | [Implemented] Considered under paper IOTC-2019-WPICMM02-06 and consultant report IOTC-2019-WPICMM02-Compliance review. | [On going] Consultant report IOTC-2019-WPICMM02-Compliance review to be reviewed by WPICMM02
3.1.4 | Provide recommendation to harmonize and streamline reporting requirements | [20 empty] | Medium | Secretariat | Simplify reporting requirements |  |  | [Implemented] WPICMM02 to make recommendations | [Implemented] WPICMM02 to make recommendations | [On going] WPICMM02 to make recommendations
4 | Develop a methodology for the assessment of implementation by CPCs, for producing the Country Compliance Reports provided annually to the Compliance Committee and flag States
4.1 | Determine significance of each CMM using a ranking measure
4.1.1 | Rank the reporting requirements of CMMs by priority (i.e which are most critical to report upon) | [20 empty] | High | Secretariat | To rank the CMMs in a way you can determine importance of compliance. |  |  | [Implemented] Considered in paper IOTC-2019-WPICMM02-07 and consultant report IOTC-2019-WPICMM02-Compliance review. | [Implemented] Considered under paper IOTC-2019-WPICMM02-07 and consultant report IOTC-2019-WPICMM02-Compliance review. | [On going] Considered under paper IOTC-2019-WPICMM02-07 and consultant report IOTC-2019-WPICMM02-Compliance review. | Establish ToR by end of september
4.1.2 | Attribute a co-efficient to determine rank importance | [20 empty] | High | Secretariat |  |  |  | [Implemented] Considered in paper IOTC-2019-WPICMM02-07 and consultant report IOTC-2019-WPICMM02-Compliance review. | [Implemented] Considered under paper IOTC-2019-WPICMM02-07 and consultant report IOTC-2019-WPICMM02-Compliance review. | [On going] Considered under paper IOTC-2019-WPICMM02-07 and consultant report IOTC-2019-WPICMM02-Compliance review. | Merged with 3
4.1.2 | WPICMM consider the report of the Secretariat to provide recommendations to the Compliance Committee | [20 empty] | High | WPICMM |  |  |  | [Implemented] WPICMM02 make recommendations | [Implemented] WPICMM02 make recommendations | [On going] WPICMM02 to make recommendations
5 | Review and assess the effectiveness and practical aspects of implementation of CMMs adopted by the Commission in order to identify deficiencies and implementation constraints faced by CPCs, and to recommend options for amendments
5.1 | Determine which CMMs are over due on assessment or no longer valid
5.1.1 | Secretariat provides paper on validity of CMMs to the WPICMM | [20 empty] | High | Secretariat | Ensure highest priorities reviewed first |  |  | [Pending] Paper for WPICMM05 | [Pending] Paper for WPICMM04 | [Pending] Paper for WPICMM03 | Paper for WPICMM02
5.1.2 | Provide recommendations to the Compliance Committee | [20 empty] | High | WPICMM |  |  |  | [Pending] WPICMM05 to make recommendations to the Compliance Committee. | Same as above | Same as above
5.2 | Conduct reviews
5.2.1 | Review each CMM using dashboard and reports | [20 empty] | High | WPICMM | Streamline reporting requirements |  |  | [Implemented] Considered in paper IOTC-2019-WPICMM02-06 and consultant report IOTC-2019-WPICMM02-Compliance review. | [Implemented] Considered under paper IOTC-2019-WPICMM02-06 and consultant report IOTC-2019-WPICMM02-Compliance review. | [On going] Considered under paper IOTC-2019-WPICMM02-06 and consultant report IOTC-2019-WPICMM02-Compliance review.
5.2.2 | Use CPCs compliance reports from part 1 to identify constraints | [20 empty] | High | WPICMM | Streamline reporting requirements |  |  | [Implemented] Considered in paper IOTC-2019-WPICMM02-06 and consultant report IOTC-2019-WPICMM02-Compliance review. | [Implemented] Considered under paper IOTC-2019-WPICMM02-06 and consultant report IOTC-2019-WPICMM02-Compliance review. | [On going] Considered under paper IOTC-2019-WPICMM02-06 and consultant report IOTC-2019-WPICMM02-Compliance review.
5.2.3 | Analyse baseline data compared to current data to review effectiveness. | [20 empty] | High | WPICMM | Streamline reporting requirements |  | 1. Where applicable taking into account incomplete baseline data and where revelant provide recommendations to the Scientific Committee to take into consideration skewed data due to improve data collection, 2) Could use estimated data if you don’t have full baseline data | [Implemented] Considered in paper IOTC-2019-WPICMM02-06 and consultant report IOTC-2019-WPICMM02-Compliance review. | [Implemented] Considered under paper IOTC-2019-WPICMM02-06 and consultant report IOTC-2019-WPICMM02-Compliance review. | [On going] Considered under paper IOTC-2019-WPICMM02-06 and consultant report IOTC-2019-WPICMM02-Compliance review.
5.2.4 | Provide recommendations to the Compliance Committee | [20 empty] | High | WPICMM | Streamline reporting requirements |  | (Could use estimated data if you don’t have full baseline data) | [Implemented] WPICMM02 makes recommendations | [Implemented] WPICMM02 makes recommendations | [On going] WPICMM02 to make recommendations
6 | Propose actions to address deficiencies in implementation
6.1 | Capacity building
6.1.1 | Identify weakeness of CPCs in capacity and ability to comply with reporting requirements | [20 empty] | High | Secretariat | Build capactiy in the CPCs |  |  | [Pending] Postponed to WPICMM05 | [Pending] Postponed to WPICMM04 | [Pending] Postponed to WPICMM03
6.1.2 | Recommend training events by IOTC compliance officers to CPCs with most need (should be regular) | [20 empty] | High | WPICMM | Build capactiy in the CPCs |  | Implementation by the Secretariat | [On going] Training under the external assistance of SWIOFISH2. | [On going] SWIOFISH 2 WB and EU Grant 304 | [On going] SWIOFISH 2 WB and WWF (VMS study) and EU Grant 304 and tuna ABNJ project Provide paper to WPICMM02 | On going SWIOFISH 2 WB and WWF (VMS study) and EU Grant 304 Provide paper to WPICMM02
6.1.3 | Recommend exchange programmes to increase skills in CPCs | [20 empty] | High | WPICMM | Build capactiy in the CPCs |  | Implementation by the Secretariat | [On going] PSM exchange implemented since 2019 (SWIOFISH2). On hold due to Covid 19. | [On going] PSM exchange implemented since 2019 (SWIOFISH2). | [Pending] Postponed to WPICMM03
6.1.4 | Recommend the establishment of a permanent capacity building mechanism | [20 empty] | High | WPICMM | Build capactiy in the CPCs |  | Implementation by the Secretariat | [Pending] Postponed to WPICMM05. | [Pending] Postponed to WPICMM03 or 04 | [Pending] Postponed to WPICMM03
6.1.5 | Recommend outreach to fishing captains/masters to educate on CMMs and to gather information on problems with implementation | [20 empty] | High | WPICMM | Build capactiy in the CPCs |  | Implementation by the Secretariat | [Pending] Postponed to WPICMM05. | [Pending] Postponed to WPICMM03 or 04 | [Pending] Postponed to WPICMM03
6.2 | Increase funding opportunities of CPCs
6.1.2 | Identify funding sources from potential donors to facilitate opportunities for funding capacty building | [20 empty] | High | Secretariat | Build capactiy in the CPCs |  |  | [On going] SWIOFISH2, EU Grant, tuna ABNJ project and WWF. | [On going] SWIOFISH 2 WB and EU Grant 304 and tuna ABNJ project | [On going] SWIOFISH 2 WB and WWF (VMS study) and EU Grant 304 and tuna ABNJ project Provide paper to WPICMM02
7 | Development of minimum regional standards for implementation of CMMs | [20 empty] | High
7.1 | Asses CPCs implementation capacity for CMMs
7.1.1 | Develop a tool and collect data from CPCs on their current implementation (status/procedures and capacity) of CMMs | [20 empty] | High | Secretariat, (WPICMM and consultant) |  |  | To be implemented through e-MARIS | [On going] This activity is being implemented under the e-MARIS project. Three IT experts have been recruited by SWIOFISH2. The e-MARIS project is currently in the Phase III Construction, which is expected to produce the following deliverables: • e-Maris Release V1 • online Record of Authorised Vessels | [On going] To be implemented under e-MARIS Recruitment of 3 IT experts by SWIOFISH2/IOC In 2019. | [Pending] To be implemented under e-MARIS Recruitment of 2 IT experts by SWIOFISH/IOC ongoing | To be implemented through e-MARIS
7.1.2 | Analyze data and produce reporting requirements from all CPCs for implementation of CMMs | [20 empty] | High | Secretariat, (WPICMM and consultant) |  |  | To be implemented through e-MARIS | [On going] This activity is being implemented under the e-MARIS project. Three IT experts have been recruited by SWIOFISH2. The e-MARIS project is currently in the Phase III Construction, which is expected to produce the following deliverables: • e-Maris Release V1 • online Record of Authorised Vessels | [On going] To be implemented under e-MARIS Recruitment of 3 IT experts by SWIOFISH2/IOC In 2019. | [Pending] To be implemented under e-MARIS Recruitment of 2 IT experts by SWIOFISH/IOC ongoing | To be implemented through e-MARIS
7.2 | Prepare the minimum IOTC standards
7.2.1 | Identify CMMs where IOTC standards have not been introduced and propose recommendation for inclusion of IOTC standard for CMMs | [20 empty] | High | Secretariat, (consultant) |  |  |  | [Implemented] Considered in paper IOTC-2019-WPICMM02-08 and consultant report IOTC-2019-WPICMM02-Compliance review. | [Implemented] Considered under paper IOTC-2019-WPICMM02-08 and consultant report IOTC-2019-WPICMM02-Compliance review. | [On going] Considered under paper IOTC-2019-WPICMM02-08 and consultant report IOTC-2019-WPICMM02-Compliance review. | Part of ToR under 3
7.2.2 | Provide recommendation to the Compliance Committe (CoC) on Resolution(s) to amend | [20 empty] | High | WPICMM |  |  |  | [Implemented] Considered in paper IOTC-2019-WPICMM02-08 and consultant report IOTC-2019-WPICMM02-Compliance review. | [Implemented] Considered under paper IOTC-2019-WPICMM02-08 and consultant report IOTC-2019-WPICMM02-Compliance review. | [On going] Considered under paper IOTC-2019-WPICMM02-08 and consultant report IOTC-2019-WPICMM02-Compliance review. | Part of ToR under 3
7.2.3 | Develop minimum regional standards for implementation of CMMs | [20 empty] | High | WPICMM |  |  |  | [Implemented] Considered in paper IOTC-2019-WPICMM02-08 and consultant report IOTC-2019-WPICMM02-Compliance review. | [Implemented] Considered under paper IOTC-2019-WPICMM02-08 and consultant report IOTC-2019-WPICMM02-Compliance review. | [On going] Considered under paper IOTC-2019-WPICMM02-08 and consultant report IOTC-2019-WPICMM02-Compliance review. | Request to be submitted to CoC16
7.2.4 | Request clarification to the Compliance on the develop minimum regional standards for implementation of CMMs | [20 empty] | High | WPICMM |  |  |  | [Implemented] Considered in paper IOTC-2019-WPICMM02-08 and consultant report IOTC-2019-WPICMM02-Compliance review. | [Implemented] Considered under paper IOTC-2019-WPICMM02-08 and consultant report IOTC-2019-WPICMM02-Compliance review. | [On going] Considered under paper IOTC-2019-WPICMM02-08 and consultant report IOTC-2019-WPICMM02-Compliance review. | Request to be submitted to CoC16
8 | Develop a harmonized assessment criteria to identify vessels presumed to have engaged in illegal, unreported and unregulated (IUU) fishing activities
8.1.1 | Establish a baseline for IUU fishing activities based on International recommendations | [20 empty] | Medium | WPICMM |  |  |  | [Implemented] Considered in paper IOTC-2019-WPICMM02-09 and consultant report IOTC-2019-WPICMM02-Compliance review. | [Implemented] Considered under paper IOTC-2019-WPICMM02-09 and consultant report IOTC-2019-WPICMM02-Compliance review. | [On going] Considered under paper IOTC-2019-WPICMM02-09 and consultant report IOTC-2019-WPICMM02-Compliance review. | Compare International instruments & IPOA IUU definitions with definitions in 17/03 to prepare a paper for WPICMM02
8.1.2 | Gather information from CPCs on their National legislation on how IUU -fishing vessels determined against the Resolution 17/03 | [20 empty] | Medium | secretariat, (consultant) |  |  |  | [Pending] Defer to 2022 (Priority medium) | [Pending] Defer to 2021 (Priority medium) | [Pending] Defer to 2019 (Priority medium) | Defer to 2019 (Priority medium)
8.1.3 | Review the assessment criteria for identifying vessel presumed to have engaged in IUU fishing activities | [20 empty] | Medium | WPICMM |  |  | To be developed by Secretariat | [Pending] Defer to 2022 (Priority medium) | [Pending] Defer to 2021 (Priority medium) | [Pending] Defer to 2019 (Priority medium)
8.1.4 | Request clarification to the Compliance on the Developent a harmonized assessment criteria for identifying vessel presumed to have engaged in IUU fishing activities | [20 empty] | Medium | WPICMM |  |  |  | [Implemented] Consultant report IOTC-2019-WPICMM02-Compliance review. | [On going] Consultant report IOTC-2019-WPICMM02-Compliance review. | [Pending] Request to be submitted to CoC16 | Request to be submitted to CoC16
9 | Monitor the development of, and recommend further actions for the IOTC list of vessels presumed to have engaged in illegal, unreported and unregulated (IUU) fishing activities, including where requested by the Compliance Committee or involved CPCs, a review of the evidence to be presented, where such evidence can be made available to the WPICMM
9.1 | Actions for the IOTC list of vessels presumed to have engaged in illegal, unreported and unregulated (IUU)
9.1.1 | Review of the evidence to be presented, where such evidence can be made available to the WPICMM | [20 empty] | High | WPICMM |  |  | This activity is only possible after the draft presumed IUU vessels list is published | [Pending] Timing issue between the WPICMM and availability of draft IUU list | [Pending] Timing issue between the WPICMM and availability of draft IUU list | [Pending] Timing issue between the WPICMM and avaiability of draft IUU list
9.1.2 | Recommend actions for the CoC on the list of vessels presumed to have engaging in IUU fishing activities, including where requested by the Compliance Committee or involved CPCs, | [20 empty] | High | WPICMM |  |  |  | [Pending] Timing issue between the WPICMM and availability of draft IUU list | [Pending] Timing issue between the WPICMM and availability of draft IUU list | [Pending] Timing issue between the WPICMM and avaiability of draft IUU list
9.1.3 | Monitor the development of recommended actions on the vessels that have been commited IUU | [20 empty] | High | WPICMM |  |  |  | [Pending] Timing issue between the WPICMM and availability of draft IUU list | [Pending] Timing issue between the WPICMM and availability of draft IUU list | [Pending] Timing issue between the WPICMM and avaiability of draft IUU list
10 | Monitor the development of, and recommend actions for the list of Large Scale Tuna Longline Vessels (LSTLVs)/carrier vessels presumed to have committed infractions of IOTC CMMs, as recorded by observers deployed under the at-sea transhipment programme | [20 empty] | Medium
10.1 | List of possible infractions under the ROP
10.1.1 | Review of the evidence to be presented on vessels presumed to have committed the infractions | [20 empty] | Medium | WPICMM |  |  | This activity is only possible after the list of vessels presumed to have committed infraction is make availible to the Working Party | [On going] Presented in paper IOTC-2021-WPICMM04-04b. | [On going] Presented under paper IOTC-2020-WPICMM03-08 | [Pending] Timing issue between the WPICMM and avaiability of list of vessels presumed to have committed infractions
10.1.2 | Request for further evidence from the CPCs on the list of vessels presumed to have committed infractions | [20 empty] | Medium | WPICMM (Secrtariat) |  |  |  | [On going] Presented in paper IOTC-2021-WPICMM04-04b. | [On going] Presented under paper IOTC-2020-WPICMM03-08 | [Pending] Timing issue between the WPICMM and avaiability of list of vessels presumed to have committed infractions
10.1.3 | Recommend actions for the CoC on the list of vessels presumed to have committed infractions | [20 empty] | Medium | WPICMM |  |  |  | [On going] Presented in paper IOTC-2021-WPICMM04-04b. | [On going] Presented under paper IOTC-2020-WPICMM03-08 | [Pending] Timing issue between the WPICMM and avaiability of list of vessels presumed to have committed infractions
10.1.4 | Monitor the development of recommended actions on the vessels that have committed infractions | [20 empty] | Medium | WPICMM |  |  |  | [On going] Presented in paper IOTC-2021-WPICMM04-04b. | [Pending] To be implemented from WPICMM04 onwards. | [Pending] Timing issue between the WPICMM and avaiability of list of vessels presumed to have committed infractions
10.1.5 | Recommend that the list of possible infraction under the ROP is presented to the WPICMM | [20 empty] | Medium | WPICMM |  |  |  | [On going] Presented in paper IOTC-2021-WPICMM04-04a & 4b. | [On going] Presented under paper IOTC-2020-WPICMM03-08 | [Pending] Timing issue between the WPICMM and avaiability of list of vessels presumed to have committed infractions
11 | Provide recommendations to the Compliance Committee to assist CPCs in the design and implementation of national MCS systems
11.1 | Design and implementation of national MCS systems
11.1.1 | Define minumum MCS requirment for relevant CMMs | [20 empty] | High | Secratariat |  |  |  | [Implemented] Considered in paper IOTC-2019-WPICMM02-05a and b and consultant report IOTC-2019-WPICMM02-VMS, MCS, CDS study | [Implemented] Considered under paper IOTC-2019-WPICMM02-05a and b and consultant report IOTC-2019-WPICMM02-VMS, MCS, CDS study | [On going] Considered under paper IOTC-2019-WPICMM02-05a and b and consultant report IOTC-2019-WPICMM02-VMS, MCS, CDS study | Part of the MCS Study outcome/recommendations
11.1.2 | CPCs to provide a report/paper on their national MCS programs | [20 empty] | High | WPICMMM (Secratariat) |  |  | Secretariat develop a template report and circulated to all CPCs for endorsement | [Implemented] Paper IOTC-2020-WPICMM03-05. | [On going] 31st December 2019 deadline for CPC to submit report on their MCS program. Information provided in paper IOTC-2020-WPICMM03-05. | [On going] Considered under paper IOTC-2019-WPICMM02-10 | To build template report and present it at WPICMM02
11.1.3 | Draft a ToR for evaluation and formulation of CPCs national MCS programs (New action WIPCMM03) | [20 empty] | High | Secretariat |  |  | Secretariat Develop draft ToR and circulate to all CPC for comments for the next CoC | [Pending] Postponed to WPICMM05. | [On going] Considered under IOTC-2020-WPICMM03-05 - Template national MCS report. | [Pending] WPICMM03 to make recommendations
11.1.4 | Evaluation of CPCs national MCS programs against the minimum requirment for CMMs | [20 empty] | High | WPICMMM (Secratariat) |  |  |  | [Implemented] Paper IOTC-2020-WPICMM03-05 - Template national MCS report. | [On going] Considered in IOTC-2020-WPICMM03-05 - Template national MCS report. | [Pending] CPCs to cmplete natinal MCS report for WPICMM03
11.1.5 | Provide recommendations to the Compliance Committee to assist CPCs in the design and implementation of national MCS systems based on their capacity and need | [20 empty] | High | WPICMMM |  |  |  | [On going] Considered under IOTC-2020-WPICMM03-05 - Template national MCS report. | [On going] Considered under IOTC-2020-WPICMM03-05 - Template national MCS report. | [Pending] WPICMM03 to make recommendations
11.1.6 | Refine the minimum requirement taking into account the result of the evaluation in 11.1.3 (New action WIPCMM03) | [20 empty] | High | WPICMM |  |  |  | [Implemented] Considered under paper IOTC-2019-WPICMM02-08 and consultant report IOTC-2019-WPICMM02-Compliance review. | [Implemented] Considered under paper IOTC-2019-WPICMM02-08 and consultant report IOTC-2019-WPICMM02-Compliance review.
12 | Provide recommendations to the Compliance Committee to assist CPCs in the design and implementation of enforcement actions to ensure compliance with IOTC CMMs
12.1 | Assist CPCs in the design and implementation of enforcement actions
12.1.1 | Develop ToRs for assessment study of CPCs capacities on design and implementation of enforcement actions by the WPICMM | [20 empty] | High | WPICMM | Develop ToRs | ToRs for the study |  | Pending] Postponed to WPICMM05 | Pending] Postponed to WPICMM04 | [Pending] Postponed to WPICMM03
12.1.2 | Conduct baseline capacity assessment of CPCs on design and implementation of enforcement actions | [20 empty] | High | Secretariat | Assess the CPCs status and capacity to design and implement enforcement actions | Baseline study report |  | Pending] Postponed to WPICMM05 | Pending] Postponed to WPICMM04 | [Pending] Postponed to WPICMM03
12.1.3 | Assessment of the report by the WPICMM | [20 empty] | High | WPICMM | Assess the Baseline study report | WPICMM assessment report |  | Pending] Postponed to WPICMM05 | Pending] Postponed to WPICMM04 | [Pending] Postponed to WPICMM03
12.1.4 | Submission of recommendations to the Compliance Committee (CoC) | [20 empty] | High | WPICMM | Provide recommendations to the CoC | WPICMM recommendations report |  | Pending] Postponed to WPICMM05 | Pending] Postponed to WPICMM04 | [Pending] Postponed to WPICMM03
13 | Development of regional capacity building mechanisms to assist CPCs to meet the regional minimum terms and conditions or standards for implementation of the CMMs
13.1 | Regional capacity building mechanisms
13.1.1 | Development of the Minimum Terms and Conditions/ Standards by the WPICMM | [20 empty] | High | WPICMM | Develop the minimum standards | Draft Minimum Standards |  | Pending] Postponed to WPICMM05 | Pending] Postponed to WPICMM04 | [Pending] Postponed to WPICMM03
13.1.2 | Submission of the Draft Minimum Terms and Conditions to the Compliance Committee | [20 empty] | High | CoC | Discuss and recommend minimum standards | Recommended minimum standards |  | Pending] Postponed to WPICMM05 | Pending] Postponed to WPICMM04 | [Pending] Postponed to WPICMM03
13.1.3 | Draft the terms of reference for the regional capacity building mechanism | [20 empty] | Higfh | WPICMM | Determine the criteria and functioning of the mechanism | Draft ToRs |  | Pending] Postponed to WPICMM05 | Pending] Postponed to WPICMM04 | [Pending] Postponed to WPICMM03
13.1.4 | Submission of the ToRs to the Compliance Committee | [20 empty] | High | CoC | Submit the Draft ToRs |  |  | Pending] Postponed to WPICMM05 | Pending] Postponed to WPICMM04 | [Pending] Postponed to WPICMM03
14 | Provide recommendations for the strengthening of the implementation of CMMs and capacity building activities, including compliance support missions, regional/national training courses and workshops, to be funded under the special fund for capacity building or extra budgetary contributions
14.1 | Strengthening of the implementation of CMMs and capacity building activities
14.1.1 | Develop ToRs for the assessment of CPCs on performance and capacity on implementation of CMMs and capacity building activities | [20 empty] | High | WPICMM | Develop ToRs | ToRs for the study |  | [On going] For assessment paper IOTC-2021-WPICMM04-04 - Assessment criteria Compliance Mission and support materials (e.g. CMMS manuals, Implementation Sheets). | [Pending] Postponed to WPICMM04 | [Pending] Postponed to WPICMM03
14.1.2 | Conduct baseline assessment of CPCs on performance and capacity on implementation of CMMs and capacity building activities | [20 empty] | High | Secretariat | Assess the CPCs status and capacity to design and implement enforcement actions | Baseline study report |  | [On going] For assessment paper IOTC-2021-WPICMM04-04 - Assessment criteria Compliance Mission and support materials (e.g. CMMS manuals, Implementation Sheets). | [Pending] Postponed to WPICMM04 | [Pending] Postponed to WPICMM03 | See 14.1.1 - ToR to be drafted in 2019 for review of WPICMM03
14.1.3 | Assessment of the report by the WPICMM | [20 empty] | High | WPICMM | Assess the Baseline study report | WPICMM assessment report |  | [On going] Paper IOTC-2021-WPICMM04-05 Assessment of CPCs on performance and implementation of CMMs. | [Pending] Brought to the attention of WPICMM032 that timeline incorrect and need to be change and in line with 14.1.1 | Bring to the attention of WPICMM02 that timeline incorrect and need to be change and in line with 14.1.1 | Bring to the attention of WPICMM02 that timeline incorrect and need to be change and in line with 14.1.1
14.1.4 | Submission of recommendations to the Compliance Committee | [20 empty] | High | WPICMM | Provide recommendations to the CoC | WPICMM recommendations report |  | [Pending] WPICMM04 to provide recommendations on capacity building and training interventions to the CoC18. | [Pending] Brought to the attention of WPICMM032 that timeline incorrect and need to be change and in line with 14.1.1 | Bring to the attention of WPICMM02 that timeline incorrect and need to be change and in line with 14.1.1 | Bring to the attention of WPICMM02 that timeline incorrect and need to be change and in line with 14.1.1
14.1.5 | Recommendation for Capacity building and training interventions based on needs and gaps identified by Secretariat from the previous country mission reports | [20 empty] | High | Secretariat, WPICMM | Train and capacity build CPCs | Training reports | Verify if action not duplicated | [On going] For example compliance missions and support materials (https://iotc.org/compliance/capacity-building-compliance ). | [Pending] Brought to the attention of WPICMM032 that timeline incorrect and need to be change and in line with 14.1.1 | Bring to the attention of WPICMM02 that timeline incorrect and need to be change and in line with 14.1.1 | Bring to the attention of WPICMM02 that timeline incorrect and need to be change and in line with 14.1.1
15 | Develop recommendations and guidelines for a schedule of sanctions for non-compliance with IOTC CMMs for consideration by the CPCs and the Commission
15.1 | Schedule of sanctions for non-compliance with IOTC CMMs
15.1.1 | Develop ToRs for a Comparative assessment of existing sanctioning systems in other orgnizations | [20 empty] | High | WPICMM | Develop ToRs | ToRs for the study |  | [Pending] Under WPICMM05 | [Pending] Under WPICMM04 | [Pending] Under WPICMM03
15.1.2 | Conduct assessment of existing sanctioning systems in other organizations | [20 empty] | High | Secretariat, WPICMM | Condcut study on sanctioning systems in the other organizations | Assessment report |  | [Pending] Under WPICMM05 | [Pending] Under WPICMM04 | [Pending] Under WPICMM03
15.1.3 | Assessment of the report and provision of recommendations by the WPICMM | [20 empty] | High | WPICMM | Assessment of report and provision of recommendations | Recommndations on the report |  | [Pending] Under WPICMM05 | [Pending] Under WPICMM04 | [Pending] Under WPICMM03
15.1.4 | Submission of the report to the Compliance Committee | [20 empty] | High | CoC | Endorsement of the report | Endorsed report |  | [Pending] Under WPICMM05 | [Pending] Under WPICMM04 | [Pending] Under WPICMM03
16 | Review compliance with data reporting obligations by CPCs and recommend actions for implementation
16.1 | Data reporting obligations by CPCs
16.1.1 | Preparation of report by the Secretariat on levels of compliance with data reporting obligations | [20 empty] | High | Secretariat | Provide report of compliance with data reporting obligations | Data Reporting Compliance levels report |  | [Pending] Under WPICMM05 | [Pending] Postponed to WPICMM04 | [Pending] Postponed to WPICMM03
16.1.2 | Assessment of the report and provision of recommendations by the WPICMM | [20 empty] | High | WPICMM | Assessment of report and provision of recommendations | Recommndations on the report |  | [Pending] Under WPICMM05 | [Pending] Postponed to WPICMM04 | [Pending] Postponed to WPICMM03
16.1.3 | Submission of the recommendations to the Compliance Committee | [20 empty] | High | CoC | Endorsement of the report | Endorsed report |  | [Pending] Under WPICMM05 | [Pending] Postponed to WPICMM04 | [Pending] Postponed to WPICMM03
17 | Review of the glossary of definitions and key terms used in IOTC Resolutions
17.1 | Glossary of definitions and terms
17.1.1 | CPCs to review the terms and definitions and provide comments on each definition | [20 empty] | High | CPCs |  |  | Deadline for submission of comments 31/12/2018, Secretariat to remind CPCs. | [On going] Paper IOTC-2020-WPICMM03-06 - Review glossary terms definitions. CoC17.35 (Para 133) The CoC RECOMMENDED that work on the glossary of definitions and key terms to be used in IOTC Resolutions be suspended and that the relevance of this exercise be reconsidered by the Compliance Committee once the work on the legal scrubbing is completed. CoC17.36 (Para 134) The CoC RECOMMENDED amendments to the timeline of the roadmap (Appendix 8/ Circular-2021-05) to conduct the legal scrubbing for consideration of the Commission for adoption. | [On going] Considered under paper IOTC-2020-WPICMM03-06 - Review glossary terms definitions | [On going] Considered under paper IOTC-2019-WPICMM02-11 | Remind CPCs by end of September See other actions and paper to be prepared for WPICMM02
17.1.2 | Secretariat to produce a consolidated list or comments received by CPCs on the Glossary | [20 empty] | High | Secretariat |  |  |  | [On going] Paper IOTC-2020-WPICMM03-06 - Review glossary terms definitions. CoC17.35 (Para 133) The CoC RECOMMENDED that work on the glossary of definitions and key terms to be used in IOTC Resolutions be suspended and that the relevance of this exercise be reconsidered by the Compliance Committee once the work on the legal scrubbing is completed. CoC17.36 (Para 134) The CoC RECOMMENDED amendments to the timeline of the roadmap (Appendix 8/ Circular-2021-05) to conduct the legal scrubbing for consideration of the Commission for adoption. | [On going] Considered under paper IOTC-2020-WPICMM03-06 - Review glossary terms definitions | [On going] Considered under paper IOTC-2019-WPICMM02-11
17.1.3 | WPICMM to provide a draft final glossary | [20 empty] | High | WPICMM |  |  |  | [On going] Paper IOTC-2020-WPICMM03-06 - Review glossary terms definitions. CoC17.35 (Para 133) The CoC RECOMMENDED that work on the glossary of definitions and key terms to be used in IOTC Resolutions be suspended and that the relevance of this exercise be reconsidered by the Compliance Committee once the work on the legal scrubbing is completed. CoC17.36 (Para 134) The CoC RECOMMENDED amendments to the timeline of the roadmap (Appendix 8/ Circular-2021-05) to conduct the legal scrubbing for consideration of the Commission for adoption. | [On going] Considered under paper IOTC-2020-WPICMM03-06 - Review glossary terms definitions | [On going] Considered under paper IOTC-2019-WPICMM02-11
17.1.4 | Submission of the recommendations to the Compliance Committee regarding the Glossary | [20 empty] | High | WPICMM |  |  |  | [On going] Paper IOTC-2020-WPICMM03-06 - Review glossary terms definitions. CoC17.35 (Para 133) The CoC RECOMMENDED that work on the glossary of definitions and key terms to be used in IOTC Resolutions be suspended and that the relevance of this exercise be reconsidered by the Compliance Committee once the work on the legal scrubbing is completed. CoC17.36 (Para 134) The CoC RECOMMENDED amendments to the timeline of the roadmap (Appendix 8/ Circular-2021-05) to conduct the legal scrubbing for consideration of the Commission for adoption. | [On going] Considered under paper IOTC-2020-WPICMM03-06 - Review glossary terms definitions | [On going] Considered under paper IOTC-2019-WPICMM02-11
17.2 | Legal scrubing of IOTC active Resolutions
17.2.1 | Submission of the recommendations to the Compliance Committee to conduct a Legal scrubing of IOTC active Resolutions and draft a ToR | [20 empty] | High | WPICMM |  |  |  | [Implemented] Submitted to CoC15, endorsed by Commission | [Implemented] Submitted to CoC15, endorsed by Commission | [Implemented] Submitted to CoC15, endorsed by Commission | Submitted to CoC15, endorsed by Commission
17.2.2 | WPICMM to finalise the ToR for the purpose to conduct a legal scrubing of the IOTC Resolutions | [20 empty] | High | WPICMM |  |  | Drafting of ToR by the Secretariat, presented at the session of the WPICMM | [Implemented] Considered in paper IOTC-2020-WPICMM03-07 - Legal scrubing IOTC Resolutions | [Implemented] Considered under paper IOTC-2020-WPICMM03-07 - Legal scrubing IOTC Resolutions | [On going] Considered under paper IOTC-2019-WPICMM02-12 | See 17.2.2 - Prepare a ToR to be presented to next WPICMM02 Consult WWF to contract Judith
18 | Review compliance requirements to identify reporting and implementation obligations that should be included in the Compliance Assessment Process
18.1 | iIentify reporting and implementation obligations
18.1.1 | EU to provide a draft list of compliance requirements not included in the compliance assessment process | [20 empty] | High | CPCs |  |  | Deadline for submission of comments 31/12/2018, Secretariat to remind CPCs. | [On going] Considered in paper IOTC-2020-WPICMM04-08 - Include requirements for Compliance assessment. EU to provide comprehensive proposal. | [On going] Considered in paper IOTC-2019-WPICMM02-13. EU to provide comprehensive proposal | [On going] Considered under paper IOTC-2019-WPICMM02-13 | To remind EU to provide the list
18.1.2 | Review of the list by the WPICMM | [20 empty] | High | WPICMM |  |  |  | [On going] Considered in paper IOTC-2020-WPICMM04-08 - Include requirements for Compliance assessment. EU to provide comprehensive proposal. | [On going] Considered in paper IOTC-2019-WPICMM02-13. EU to provide comprehensive proposal | [On going] Considered under paper IOTC-2019-WPICMM02-13
18.1.3 | Submission of the recommendations to the Compliance Committee to include additional reporting and implementation obligations in the Compliance Assessment Process | [20 empty] | High | WPICMM |  |  |  | [On going] WPICMM04 to provide recommendation(s) to the Compliance Committee. | [On going] Considered under paper IOTC-2019-WPICMM02-13 | [On going] Considered under paper IOTC-2019-WPICMM02-13
19 | Other tasks as assigned by the Compliance Committee or Commission
19.1 | Component
19.1.1 | Activity description | [25 empty] | N/A | N/A | N/A