## WP
WPICMM WORK PLAN (2018-2022)
Version 1: 5/7 March 2018
| Description | Q1 / 2018 | Q2 / 2018 | Q3 / 2018 | Q4 / 2018 | Q1 / 2019 | Q2 / 2019 | Q3 / 2019 | Q4 / 2019 | Q1 / 2020 | Q2 / 2020 | Q3 / 2020 | Q4 / 2020 | Q1 / 2021 | Q2 / 2021 | Q3 / 2021 | Q4 / 2021 | Q1 / 2022 | Q2 / 2022 | Q3 / 2022 | Q4 / 2022 | Priorities | Responsibility | Objective(s) | OVIs | Notes | Status 06/09/2018 | Status 15/12/2018 | Status December 2019
WPICMM Work Plan
1 | Examine all aspects of CPCs technical implementation of CMMs and recommending ways to enhance the level of implementation
1.1 | Produce dashboard of compliance with CMMs for all CPCs and have this online
1.1.1 | Create dashboard showing compliance with CMMs from national reports and put on secured part of the IOTC website so it is visible to all CPCs | [20 empty] | High | Secretariat | Creating the dashboard to have platform to check the performance of CPCs |  |  |  | [Pending] To be implemented under e-MARIS Recruitment of 2 IT experts by SWIOFISH/IOC ongoing | [Pending] To be implemented under e-MARIS Recruitment of 3 IT experts by SWIOFISH/IOC terminated in 2019. Developpement of e-MARIS started as well as online RAV.
1.1.2 | CPCs to add information to dashboard by reporting deadlines | [20 empty] | High | CPCs | To have all CPCs reporting the required information on time |  | This should be done after the complliance form is submitted- April |  | Same as above | Same as above
1.1.3 | Rank the CMMs/reporting requirements by priority (i.e which are most critical to report upon) | [20 empty] | High | Secretariat / WPICMM | To rank the CMMs in a way you can determine importance of compliance. |  |  |  | [On going] Considered under consultant report IOTC-2019-WPICMM02-Compliance review. | [Implemented] Analyses providedConsidered inunder cConsultant’s report, IOTC-2019-WPICMM02-Compliance review.
1.1.4 | Define a weighting scheme to the P/C assessment of the reporting requirements | [20 empty] | High | Secretariat / WPICMM | To define a weighting scheme for P/C |  | Secretariat to produce a weighting scheme for discussion at the WPICMM |  | Same as above | Same as above
1.2 | Prioritise CMMs with lowest implementation levels to determine common issues with compliance
1.2.1 | Use CPCs Compliance Assessment results to determine common challenges and difficulties with compliance | [20 empty] | High | Secretariat &CPCs | Identify difficulities of CPCs in complying with the resolutions |  | Send out by Q3 and return before end of Q4 | To produce paper for WPICMM02 for distribution before end of september | [On going] Considered under paper IOTC-2019-WPICMM02-04 and consultant report IOTC-2019-WPICMM02-Compliance review. | [Implemented] Considered under in paper document IOTC-2019-WPICMM02-04 and cConsultant’s report IOTC-2019-WPICMM02-Compliance review.
1.2.2 | Follow up with interviews with CPCs to gather more detail | [20 empty] | High | Secretariat | Identify difficulities of CPCs in complying with the resolutions |  |  |  | [On going] CPCs to provide more details during WPICMM02 | [Implemented] CPCs provided more details during WPICMM02
1.2.3 | Recommend a plan to improve compliance could include; specific training events, amendments to reporting requirements, data analysis assistance | [20 empty] | High | WPICMM | Solving difficulities of CPCs in complying with the resolutions |  |  |  | [On going] WPICMM02 to make recommendations | [On going] WPICMM03 to make recommendations
2 | Examine Monitoring, Control and Surveillance (MCS) technical matters in order to provide the Compliance Committee with options for strengthening MCS
2.1 | Improve IOTC MCS scheme
2.1.1 | Review CPCs national MCS scheme and current MCS practices | [20 empty] | Medium | Secretariat |  |  |  | To check with MCS consultant | [On going] Considered under paper IOTC-2019-WPICMM02-05 and consultant report IOTC-2019-WPICMM02-VMS study & IOTC-2019-WPICMM02-MCS study. | [Implemented] Considered under paper IOTC-2019-WPICMM02-05 and consultant report IOTC-2019-WPICMM02-VMS study & IOTC-2019-WPICMM02-MCS study.
2.1.2 | Review existing IOTC MCS tools | [20 empty] | Medium | Secretariat |  |  |  | Will be conducted within the MCS study | [On going] Considered under paper IOTC-2019-WPICMM02-05 and consultant report IOTC-2019-WPICMM02-VMS study & IOTC-2019-WPICMM02-MCS study. | [Implemented] Considered under paper IOTC-2019-WPICMM02-05 and consultant report IOTC-2019-WPICMM02-VMS study & IOTC-2019-WPICMM02-MCS study.
2.1.3 | Review upcoming MCS reports comprising of reports on VMS and CDS | [20 empty] | Medium | WPICMM |  |  |  |  | [On going] Report to be presented at WPICMM02 for review | [Implemented] Report presented at WPICMM02 for review
2.1.4 | Recommendation that the VMS and CDS study reports are submitted to the WPICMM | [20 empty] | Medium | WPICMM |  |  | Should be done before May when CC meets |  | [On going] Report to be presented at WPICMM02 for review | [Implemented] Report presented at WPICMM02 for review
2.1.4 | Make recommendations on these reports for the Compliance Committee | [20 empty] | Medium | WPICMM |  |  | Should be done before May when CC meets |  | [On going] WPICMM02 to make recommendations | [Implemented] WPICMM02 makes recommendations
3 | Review the reporting requirements contained within CMMs in order to harmonize and streamline
3.1 | Review reporting requrements in all CMMs
3.1.1 | Assess and compare reporting requirements for all CMMs in other relevant RFMOs and harmonize | [20 empty] | Medium | Consultant | Simplify reporting requirements |  |  | Establish ToR by end of september | [On going] Considered under paper IOTC-2019-WPICMM02-06 and consultant report IOTC-2019-WPICMM02-Compliance review. | [Implemented] Considered under paper IOTC-2019-WPICMM02-06 and consultant report IOTC-2019-WPICMM02-Compliance review.
3.1.2 | Undertake an assessment of existing IOTC reporting requirement in order to streamline the reporting by CPCs | [20 empty] | High | Secretariat | Simplify reporting requirements |  |  | See above (ToR for the two line) | [On going] Considered under paper IOTC-2019-WPICMM02-06 and consultant report IOTC-2019-WPICMM02-Compliance review. | [Implemented] Considered under paper IOTC-2019-WPICMM02-06 and consultant report IOTC-2019-WPICMM02-Compliance review.
3.1.3 | Consider the report at WPICMM | [20 empty] | Medium | WPICMM | Simplify reporting requirements |  | Make recommendations to Secretariat to complete 3.1.4 |  | [On going] Consultant report IOTC-2019-WPICMM02-Compliance review to be reviewed by WPICMM02 | [Implemented] Considered under paper IOTC-2019-WPICMM02-06 and consultant report IOTC-2019-WPICMM02-Compliance review.
3.1.4 | Provide recommendation to harmonize and streamline reporting requirements | [20 empty] | Medium | Secretariat | Simplify reporting requirements |  |  |  | [On going] WPICMM02 to make recommendations | [Implemented] WPICMM02 to make recommendations
4 | Develop a methodology for the assessment of implementation by CPCs, for producing the Country Compliance Reports provided annually to the Compliance Committee and flag States
4.1 | Determine significance of each CMM using a ranking measure
4.1.1 | Rank the reporting requirements of CMMs by priority (i.e which are most critical to report upon) | [20 empty] | High | Secretariat | To rank the CMMs in a way you can determine importance of compliance. |  |  | Establish ToR by end of september | [On going] Considered under paper IOTC-2019-WPICMM02-07 and consultant report IOTC-2019-WPICMM02-Compliance review. | [Implemented] Considered under paper IOTC-2019-WPICMM02-07 and consultant report IOTC-2019-WPICMM02-Compliance review.
4.1.2 | Attribute a co-efficient to determine rank importance | [20 empty] | High | Secretariat |  |  |  | Merged with 3 | [On going] Considered under paper IOTC-2019-WPICMM02-07 and consultant report IOTC-2019-WPICMM02-Compliance review. | [Implemented] Considered under paper IOTC-2019-WPICMM02-07 and consultant report IOTC-2019-WPICMM02-Compliance review.
4.1.2 | WPICMM consider the report of the Secretariat to provide recommendations to the Compliance Committee | [20 empty] | High | WPICMM |  |  |  |  | [On going] WPICMM02 to make recommendations | [Implemented] WPICMM02 make recommendations
5 | Review and assess the effectiveness and practical aspects of implementation of CMMs adopted by the Commission in order to identify deficiencies and implementation constraints faced by CPCs, and to recommend options for amendments
5.1 | Determine which CMMs are over due on assessment or no longer valid
5.1.1 | Secretariat provides paper on validity of CMMs to the WPICMM | [20 empty] | High | Secretariat | Ensure highest priorities reviewed first |  |  | Paper for WPICMM02 | [Pending] Paper for WPICMM03 | [Pending] Paper for WPICMM04
5.1.2 | Provide recommendations to the Compliance Committee | [20 empty] | High | WPICMM |  |  |  |  | Same as above | Same as above
5.2 | Conduct reviews
5.2.1 | Review each CMM using dashboard and reports | [20 empty] | High | WPICMM | Streamline reporting requirements |  |  |  | [On going] Considered under paper IOTC-2019-WPICMM02-06 and consultant report IOTC-2019-WPICMM02-Compliance review. | [Implemented] Considered under paper IOTC-2019-WPICMM02-06 and consultant report IOTC-2019-WPICMM02-Compliance review.
5.2.2 | Use CPCs compliance reports from part 1 to identify constraints | [20 empty] | High | WPICMM | Streamline reporting requirements |  |  |  | [On going] Considered under paper IOTC-2019-WPICMM02-06 and consultant report IOTC-2019-WPICMM02-Compliance review. | [Implemented] Considered under paper IOTC-2019-WPICMM02-06 and consultant report IOTC-2019-WPICMM02-Compliance review.
5.2.3 | Analyse baseline data compared to current data to review effectiveness. | [20 empty] | High | WPICMM | Streamline reporting requirements |  | 1. Where applicable taking into account incomplete baseline data and where revelant provide recommendations to the Scientific Committee to take into consideration skewed data due to improve data collection, 2) Could use estimated data if you don’t have full baseline data |  | [On going] Considered under paper IOTC-2019-WPICMM02-06 and consultant report IOTC-2019-WPICMM02-Compliance review. | [Implemented] Considered under paper IOTC-2019-WPICMM02-06 and consultant report IOTC-2019-WPICMM02-Compliance review.
5.2.4 | Provide recommendations to the Compliance Committee | [20 empty] | High | WPICMM | Streamline reporting requirements |  | (Could use estimated data if you don’t have full baseline data) |  | [On going] WPICMM02 to make recommendations | [Implemented] WPICMM02 makes recommendations
6 | Propose actions to address deficiencies in implementation
6.1 | Capacity building
6.1.1 | Identify weakeness of CPCs in capacity and ability to comply with reporting requirements | [20 empty] | High | Secretariat | Build capactiy in the CPCs |  |  |  | [Pending] Postponed to WPICMM03 | [Pending] Postponed to WPICMM04
6.1.2 | Recommend training events by IOTC compliance officers to CPCs with most need (should be regular) | [20 empty] | High | WPICMM | Build capactiy in the CPCs |  | Implementation by the Secretariat | On going SWIOFISH 2 WB and WWF (VMS study) and EU Grant 304 Provide paper to WPICMM02 | [On going] SWIOFISH 2 WB and WWF (VMS study) and EU Grant 304 and tuna ABNJ project Provide paper to WPICMM02 | [On going] SWIOFISH 2 WB and EU Grant 304
6.1.3 | Recommend exchange programmes to increase skills in CPCs | [20 empty] | High | WPICMM | Build capactiy in the CPCs |  | Implementation by the Secretariat |  | [Pending] Postponed to WPICMM03 | [On going] PSM exchange implemented since 2019 (SWIOFISH2).
6.1.4 | Recommend the establishment of a permanent capacity building mechanism | [20 empty] | High | WPICMM | Build capactiy in the CPCs |  | Implementation by the Secretariat |  | [Pending] Postponed to WPICMM03 | [Pending] Postponed to WPICMM03 or 04
6.1.5 | Recommend outreach to fishing captains/masters to educate on CMMs and to gather information on problems with implementation | [20 empty] | High | WPICMM | Build capactiy in the CPCs |  | Implementation by the Secretariat |  | [Pending] Postponed to WPICMM03 | [Pending] Postponed to WPICMM03 or 04
6.2 | Increase funding opportunities of CPCs
6.1.2 | Identify funding sources from potential donors to facilitate opportunities for funding capacty building | [20 empty] | High | Secretariat | Build capactiy in the CPCs |  |  |  | [On going] SWIOFISH 2 WB and WWF (VMS study) and EU Grant 304 and tuna ABNJ project Provide paper to WPICMM02 | [On going] SWIOFISH 2 WB and EU Grant 304 and tuna ABNJ project
7 | Development of minimum regional standards for implementation of CMMs | [20 empty] | High
7.1 | Asses CPCs implementation capacity for CMMs
7.1.1 | Develop a tool and collect data from CPCs on their current implementation (status/procedures and capacity) of CMMs | [20 empty] | High | Secretariat, (WPICMM and consultant) |  |  | To be implemented through e-MARIS | To be implemented through e-MARIS | [Pending] To be implemented under e-MARIS Recruitment of 2 IT experts by SWIOFISH/IOC ongoing | [On going] To be implemented under e-MARIS Recruitment of 3 IT experts by SWIOFISH2/IOC In 2019.
7.1.2 | Analyze data and produce reporting requirements from all CPCs for implementation of CMMs | [20 empty] | High | Secretariat, (WPICMM and consultant) |  |  | To be implemented through e-MARIS | To be implemented through e-MARIS | [Pending] To be implemented under e-MARIS Recruitment of 2 IT experts by SWIOFISH/IOC ongoing | [On going] To be implemented under e-MARIS Recruitment of 3 IT experts by SWIOFISH2/IOC In 2019.
7.2 | Prepare the minimum IOTC standards
7.2.1 | Identify CMMs where IOTC standards have not been introduced and propose recommendation for inclusion of IOTC standard for CMMs | [20 empty] | High | Secretariat, (consultant) |  |  |  | Part of ToR under 3 | [On going] Considered under paper IOTC-2019-WPICMM02-08 and consultant report IOTC-2019-WPICMM02-Compliance review. | [Implemented] Considered under paper IOTC-2019-WPICMM02-08 and consultant report IOTC-2019-WPICMM02-Compliance review.
7.2.2 | Provide recommendation to the Compliance Committe (CoC) on Resolution(s) to amend | [20 empty] | High | WPICMM |  |  |  | Part of ToR under 3 | [On going] Considered under paper IOTC-2019-WPICMM02-08 and consultant report IOTC-2019-WPICMM02-Compliance review. | [Implemented] Considered under paper IOTC-2019-WPICMM02-08 and consultant report IOTC-2019-WPICMM02-Compliance review.
7.2.3 | Develop minimum regional standards for implementation of CMMs | [20 empty] | High | WPICMM |  |  |  | Request to be submitted to CoC16 | [On going] Considered under paper IOTC-2019-WPICMM02-08 and consultant report IOTC-2019-WPICMM02-Compliance review. | [Implemented] Considered under paper IOTC-2019-WPICMM02-08 and consultant report IOTC-2019-WPICMM02-Compliance review.
7.2.4 | Request clarification to the Compliance on the develop minimum regional standards for implementation of CMMs | [20 empty] | High | WPICMM |  |  |  | Request to be submitted to CoC16 | [On going] Considered under paper IOTC-2019-WPICMM02-08 and consultant report IOTC-2019-WPICMM02-Compliance review. | [Implemented] Considered under paper IOTC-2019-WPICMM02-08 and consultant report IOTC-2019-WPICMM02-Compliance review.
8 | Develop a harmonized assessment criteria to identify vessels presumed to have engaged in illegal, unreported and unregulated (IUU) fishing activities
8.1.1 | Establish a baseline for IUU fishing activities based on International recommendations | [20 empty] | Medium | WPICMM |  |  |  | Compare International instruments & IPOA IUU definitions with definitions in 17/03 to prepare a paper for WPICMM02 | [On going] Considered under paper IOTC-2019-WPICMM02-09 and consultant report IOTC-2019-WPICMM02-Compliance review. | [Implemented] Considered under paper IOTC-2019-WPICMM02-09 and consultant report IOTC-2019-WPICMM02-Compliance review.
8.1.2 | Gather information from CPCs on their National legislation on how IUU -fishing vessels determined against the Resolution 17/03 | [20 empty] | Medium | secretariat, (consultant) |  |  |  | Defer to 2019 (Priority medium) | [Pending] Defer to 2019 (Priority medium) | [Pending] Defer to 2021 (Priority medium)
8.1.3 | Review the assessment criteria for identifying vessel presumed to have engaged in IUU fishing activities | [20 empty] | Medium | WPICMM |  |  | To be developed by Secretariat |  | [Pending] Defer to 2019 (Priority medium) | [Pending] Defer to 2021 (Priority medium)
8.1.4 | Request clarification to the Compliance on the Developent a harmonized assessment criteria for identifying vessel presumed to have engaged in IUU fishing activities | [20 empty] | Medium | WPICMM |  |  |  | Request to be submitted to CoC16 | [Pending] Request to be submitted to CoC16 | [On going] Consultant report IOTC-2019-WPICMM02-Compliance review.
9 | Monitor the development of, and recommend further actions for the IOTC list of vessels presumed to have engaged in illegal, unreported and unregulated (IUU) fishing activities, including where requested by the Compliance Committee or involved CPCs, a review of the evidence to be presented, where such evidence can be made available to the WPICMM
9.1 | Actions for the IOTC list of vessels presumed to have engaged in illegal, unreported and unregulated (IUU)
9.1.1 | Review of the evidence to be presented, where such evidence can be made available to the WPICMM | [20 empty] | High | WPICMM |  |  | This activity is only possible after the draft presumed IUU vessels list is published |  | [Pending] Timing issue between the WPICMM and avaiability of draft IUU list | [Pending] Timing issue between the WPICMM and availability of draft IUU list
9.1.2 | Recommend actions for the CoC on the list of vessels presumed to have engaging in IUU fishing activities, including where requested by the Compliance Committee or involved CPCs, | [20 empty] | High | WPICMM |  |  |  |  | [Pending] Timing issue between the WPICMM and avaiability of draft IUU list | [Pending] Timing issue between the WPICMM and availability of draft IUU list
9.1.3 | Monitor the development of recommended actions on the vessels that have been commited IUU | [20 empty] | High | WPICMM |  |  |  |  | [Pending] Timing issue between the WPICMM and avaiability of draft IUU list | [Pending] Timing issue between the WPICMM and availability of draft IUU list
10 | Monitor the development of, and recommend actions for the list of Large Scale Tuna Longline Vessels (LSTLVs)/carrier vessels presumed to have committed infractions of IOTC CMMs, as recorded by observers deployed under the at-sea transhipment programme | [20 empty] | Medium
10.1 | List of possible infractions under the ROP
10.1.1 | Review of the evidence to be presented on vessels presumed to have committed the infractions | [20 empty] | Medium | WPICMM |  |  | This activity is only possible after the list of vessels presumed to have committed infraction is make availible to the Working Party |  | [Pending] Timing issue between the WPICMM and avaiability of list of vessels presumed to have committed infractions | [On going] Presented under paper IOTC-2020-WPICMM03-08
10.1.2 | Request for further evidence from the CPCs on the list of vessels presumed to have committed infractions | [20 empty] | Medium | WPICMM (Secrtariat) |  |  |  |  | [Pending] Timing issue between the WPICMM and avaiability of list of vessels presumed to have committed infractions | [On going] Presented under paper IOTC-2020-WPICMM03-08
10.1.3 | Recommend actions for the CoC on the list of vessels presumed to have committed infractions | [20 empty] | Medium | WPICMM |  |  |  |  | [Pending] Timing issue between the WPICMM and avaiability of list of vessels presumed to have committed infractions | [On going] Presented under paper IOTC-2020-WPICMM03-08
10.1.4 | Monitor the development of recommended actions on the vessels that have committed infractions | [20 empty] | Medium | WPICMM |  |  |  |  | [Pending] Timing issue between the WPICMM and avaiability of list of vessels presumed to have committed infractions | [Pending] To be implemented from WPICMM04 onwards.
10.1.5 | Recommend that the list of possible infraction under the ROP is presented to the WPICMM | [20 empty] | Medium | WPICMM |  |  |  |  | [Pending] Timing issue between the WPICMM and avaiability of list of vessels presumed to have committed infractions | [On going] Presented under paper IOTC-2020-WPICMM03-08
11 | Provide recommendations to the Compliance Committee to assist CPCs in the design and implementation of national MCS systems
11.1 | Design and implementation of national MCS systems
11.1.1 | Define minumum MCS requirment for relevant CMMs | [20 empty] | High | Secratariat |  |  |  | Part of the MCS Study outcome/recommendations | [On going] Considered under paper IOTC-2019-WPICMM02-05a and b and consultant report IOTC-2019-WPICMM02-VMS, MCS, CDS study | [Implemented] Considered under paper IOTC-2019-WPICMM02-05a and b and consultant report IOTC-2019-WPICMM02-VMS, MCS, CDS study
11.1.2 | CPCs to provide a report/paper on their national MCS programs | [20 empty] | High | WPICMMM (Secratariat) |  |  | Secretariat develop a template report and circulated to all CPCs for endorsement | To build template report and present it at WPICMM02 | [On going] Considered under paper IOTC-2019-WPICMM02-10 | [On going] 31st December 2019 deadline for CPC to submit report on their MCS program. Information provided in paper IOTC-2020-WPICMM03-05.
11.1.3 | Evaluation of CPCs national MCS programs againest the minimum requirment for CMMs | [20 empty] | High | WPICMMM (Secratariat) |  |  |  |  | [Pending] CPCs to cmplete natinal MCS report for WPICMM03 | [On going] Considered in IOTC-2020-WPICMM03-05 - Template national MCS report.
11.1.4 | Provide recommendations to the Compliance Committee to assist CPCs in the design and implementation of national MCS systems based on their capacity and need | [20 empty] | High | WPICMMM |  |  |  |  | [Pending] WPICMM03 to make recommendations | [On going] Considered under IOTC-2020-WPICMM03-05 - Template national MCS report.
12 | Provide recommendations to the Compliance Committee to assist CPCs in the design and implementation of enforcement actions to ensure compliance with IOTC CMMs
12.1 | Assist CPCs in the design and implementation of enforcement actions
12.1.1 | Develop ToRs for assessment study of CPCs capacities on design and implementation of enforcement actions by the WPICMM | [20 empty] | High | WPICMM | Develop ToRs | ToRs for the study |  |  | [Pending] Postponed to WPICMM03 | Pending] Postponed to WPICMM04
12.1.2 | Conduct baseline capacity assessment of CPCs on design and implementation of enforcement actions | [20 empty] | High | Secretariat | Assess the CPCs status and capacity to design and implement enforcement actions | Baseline study report |  |  | [Pending] Postponed to WPICMM03 | Pending] Postponed to WPICMM04
12.1.3 | Assessment of the report by the WPICMM | [20 empty] | High | WPICMM | Assess the Baseline study report | WPICMM assessment report |  |  | [Pending] Postponed to WPICMM03 | Pending] Postponed to WPICMM04
12.1.4 | Submission of recommendations to the Compliance Committee (CoC) | [20 empty] | High | WPICMM | Provide recommendations to the CoC | WPICMM recommendations report |  |  | [Pending] Postponed to WPICMM03 | Pending] Postponed to WPICMM04
13 | Development of regional capacity building mechanisms to assist CPCs to meet the regional minimum terms and conditions or standards for implementation of the CMMs
13.1 | Regional capacity building mechanisms
13.1.1 | Development of the Minimum Terms and Conditions/ Standards by the WPICMM | [20 empty] | High | WPICMM | Develop the minimum standards | Draft Minimum Standards |  |  | [Pending] Postponed to WPICMM03 | Pending] Postponed to WPICMM04
13.1.2 | Submission of the Draft Minimum Terms and Conditions to the Compliance Committee | [20 empty] | High | CoC | Discuss and recommend minimum standards | Recommended minimum standards |  |  | [Pending] Postponed to WPICMM03 | Pending] Postponed to WPICMM04
13.1.3 | Draft the terms of reference for the regional capacity building mechanism | [20 empty] | Higfh | WPICMM | Determine the criteria and functioning of the mechanism | Draft ToRs |  |  | [Pending] Postponed to WPICMM03 | Pending] Postponed to WPICMM04
13.1.4 | Submission of the ToRs to the Compliance Committee | [20 empty] | High | CoC | Submit the Draft ToRs |  |  |  | [Pending] Postponed to WPICMM03 | Pending] Postponed to WPICMM04
14 | Provide recommendations for the strengthening of the implementation of CMMs and capacity building activities, including compliance support missions, regional/national training courses and workshops, to be funded under the special fund for capacity building or extra budgetary contributions
14.1 | Strengthening of the implementation of CMMs and capacity building activities
14.1.1 | Develop ToRs for the assessment of CPCs on performance and capacity on implementation of CMMs and capacity building activities | [20 empty] | High | WPICMM | Develop ToRs | ToRs for the study |  |  | [Pending] Postponed to WPICMM03 | [Pending] Postponed to WPICMM04
14.1.2 | Conduct baseline assessment of CPCs on performance and capacity on implementation of CMMs and capacity building activities | [20 empty] | High | Secretariat | Assess the CPCs status and capacity to design and implement enforcement actions | Baseline study report |  | See 14.1.1 - ToR to be drafted in 2019 for review of WPICMM03 | [Pending] Postponed to WPICMM03 | [Pending] Postponed to WPICMM04
14.1.3 | Assessment of the report by the WPICMM | [20 empty] | High | WPICMM | Assess the Baseline study report | WPICMM assessment report |  | Bring to the attention of WPICMM02 that timeline incorrect and need to be change and in line with 14.1.1 | Bring to the attention of WPICMM02 that timeline incorrect and need to be change and in line with 14.1.1 | [Pending] Brought to the attention of WPICMM032 that timeline incorrect and need to be change and in line with 14.1.1
14.1.4 | Submission of recommendations to the Compliance Committee | [20 empty] | High | WPICMM | Provide recommendations to the CoC | WPICMM recommendations report |  | Bring to the attention of WPICMM02 that timeline incorrect and need to be change and in line with 14.1.1 | Bring to the attention of WPICMM02 that timeline incorrect and need to be change and in line with 14.1.1 | [Pending] Brought to the attention of WPICMM032 that timeline incorrect and need to be change and in line with 14.1.1
14.1.5 | Recommendation for Capacity building and training interventions based on needs and gaps identified by Secretariat from the previous country mission reports | [20 empty] | High | Secretariat, WPICMM | Train and capacity build CPCs | Training reports | Verify if action not duplicated | Bring to the attention of WPICMM02 that timeline incorrect and need to be change and in line with 14.1.1 | Bring to the attention of WPICMM02 that timeline incorrect and need to be change and in line with 14.1.1 | [Pending] Brought to the attention of WPICMM032 that timeline incorrect and need to be change and in line with 14.1.1
15 | Develop recommendations and guidelines for a schedule of sanctions for non-compliance with IOTC CMMs for consideration by the CPCs and the Commission
15.1 | Schedule of sanctions for non-compliance with IOTC CMMs
15.1.1 | Develop ToRs for a Comparative assessment of existing sanctioning systems in other orgnizations | [20 empty] | High | WPICMM | Develop ToRs | ToRs for the study |  |  | [Pending] Under WPICMM03 | [Pending] Under WPICMM04
15.1.2 | Conduct assessment of existing sanctioning systems in other organizations | [20 empty] | High | Secretariat, WPICMM | Condcut study on sanctioning systems in the other organizations | Assessment report |  |  | [Pending] Under WPICMM03 | [Pending] Under WPICMM04
15.1.3 | Assessment of the report and provision of recommendations by the WPICMM | [20 empty] | High | WPICMM | Assessment of report and provision of recommendations | Recommndations on the report |  |  | [Pending] Under WPICMM03 | [Pending] Under WPICMM04
15.1.4 | Submission of the report to the Compliance Committee | [20 empty] | High | CoC | Endorsement of the report | Endorsed report |  |  | [Pending] Under WPICMM03 | [Pending] Under WPICMM04
16 | Review compliance with data reporting obligations by CPCs and recommend actions for implementation
16.1 | Data reporting obligations by CPCs
16.1.1 | Preparation of report by the Secretariat on levels of compliance with data reporting obligations | [20 empty] | High | Secretariat | Provide report of compliance with data reporting obligations | Data Reporting Compliance levels report |  |  | [Pending] Postponed to WPICMM03 | [Pending] Postponed to WPICMM04
16.1.2 | Assessment of the report and provision of recommendations by the WPICMM | [20 empty] | High | WPICMM | Assessment of report and provision of recommendations | Recommndations on the report |  |  | [Pending] Postponed to WPICMM03 | [Pending] Postponed to WPICMM04
16.1.3 | Submission of the recommendations to the Compliance Committee | [20 empty] | High | CoC | Endorsement of the report | Endorsed report |  |  | [Pending] Postponed to WPICMM03 | [Pending] Postponed to WPICMM04
17 | Review of the glossary of definitions and key terms used in IOTC Resolutions
17.1 | Glossary of definitions and terms
17.1.1 | CPCs to review the terms and definitions and provide comments on each definition | [20 empty] | High | CPCs |  |  | Deadline for submission of comments 31/12/2018, Secretariat to remind CPCs. | Remind CPCs by end of September See other actions and paper to be prepared for WPICMM02 | [On going] Considered under paper IOTC-2019-WPICMM02-11 | [On going] Considered under paper IOTC-2020-WPICMM03-06 - Review glossary terms definitions
17.1.2 | Secretariat to produce a consolidated list or comments received by CPCs on the Glossary | [20 empty] | High | Secretariat |  |  |  |  | [On going] Considered under paper IOTC-2019-WPICMM02-11 | [On going] Considered under paper IOTC-2020-WPICMM03-06 - Review glossary terms definitions
17.1.3 | WPICMM to provide a draft final glossary | [20 empty] | High | WPICMM |  |  |  |  | [On going] Considered under paper IOTC-2019-WPICMM02-11 | [On going] Considered under paper IOTC-2020-WPICMM03-06 - Review glossary terms definitions
17.1.4 | Submission of the recommendations to the Compliance Committee regarding the Glossary | [20 empty] | High | WPICMM |  |  |  |  | [On going] Considered under paper IOTC-2019-WPICMM02-11 | [On going] Considered under paper IOTC-2020-WPICMM03-06 - Review glossary terms definitions
17.2 | Legal scrubing of IOTC active Resolutions
17.2.1 | Submission of the recommendations to the Compliance Committee to conduct a Legal scrubing of IOTC active Resolutions and draft a ToR | [20 empty] | High | WPICMM |  |  |  | Submitted to CoC15, endorsed by Commission | [Implemented] Submitted to CoC15, endorsed by Commission | [Implemented] Submitted to CoC15, endorsed by Commission
17.2.2 | WPICMM to finalise the ToR for the purpose to conduct a legal scrubing of the IOTC Resolutions | [20 empty] | High | WPICMM |  |  | Drafting of ToR by the Secretariat, presented at the session of the WPICMM | See 17.2.2 - Prepare a ToR to be presented to next WPICMM02 Consult WWF to contract Judith | [On going] Considered under paper IOTC-2019-WPICMM02-12 | [Implemented] Considered under paper IOTC-2020-WPICMM03-07 - Legal scrubing IOTC Resolutions
18 | Review compliance requirements to identify reporting and implementation obligations that should be included in the Compliance Assessment Process
18.1 | iIentify reporting and implementation obligations
18.1.1 | EU to provide a draft list of compliance requirements not included in the compliance assessment process | [20 empty] | High | CPCs |  |  | Deadline for submission of comments 31/12/2018, Secretariat to remind CPCs. | To remind EU to provide the list | [On going] Considered under paper IOTC-2019-WPICMM02-13 | [On going] Considered in paper IOTC-2019-WPICMM02-13. EU to provide comprehensive proposal
18.1.2 | Review of the list by the WPICMM | [20 empty] | High | WPICMM |  |  |  |  | [On going] Considered under paper IOTC-2019-WPICMM02-13 | [On going] Considered in paper IOTC-2019-WPICMM02-13. EU to provide comprehensive proposal
18.1.3 | Submission of the recommendations to the Compliance Committee to include additional reporting and implementation obligations in the Compliance Assessment Process | [20 empty] | High | WPICMM |  |  |  |  | [On going] Considered under paper IOTC-2019-WPICMM02-13 | [On going] Considered under paper IOTC-2019-WPICMM02-13
19 | Other tasks as assigned by the Compliance Committee or Commission
19.1 | Component
19.1.1 | Activity description | [26 empty] | N/A | N/A